## 📋 Project Overview
⬡ DEBLOATKIT v1.0 — Project Overview
Samsung Galaxy Debloater for Windows · TeamExyKings · Yashwanth Ram Somireddy · MIT License
PROJECT IDENTITY
App Name | DebloatKit
Version | v1.0
Subtitle | Works with Samsung Galaxy Devices
Author | Yashwanth Ram Somireddy
Brand | TeamExyKings
Location | Chennai, India
License | MIT — Free & Open Source
Platform | Windows 10 / 11
Language | Python 3.11+
UI Framework | CustomTkinter 6.0+
ADB Method | subprocess — --user 0 only, no root
GitHub | https://github.com/yashwanthramsomireddy/DebloatKit
PayPal | https://paypal.me/yash92duster
Razorpay | https://rzp.io/rzp/nsogoeD
Started | 2026-08-28
Status | Active — v1.0 Released
TECH STACK
Component | Technology | Version | Purpose | Notes
UI Framework | CustomTkinter | 6.0+ | Dark-theme desktop GUI | Built on tkinter
Language | Python | 3.11+ | Core application logic | Type hints, threading
ADB Bridge | subprocess | stdlib | Execute ADB shell commands | No root, --user 0 only
Package DB | JSON | custom | 110+ packages, risk ratings | Editable without code changes
Backup Engine | json (stdlib) | stdlib | Timestamped backup/restore | Stored in /backups/
Threading | threading | stdlib | Non-blocking ADB operations | Daemon threads
Distribution | PyInstaller | 6.x | Single .exe for Windows | --onefile --windowed
Installer | Inno Setup | 6.x | Windows setup .exe | License agreement included
PACKAGE DATABASE
Category | Count | Risk Levels | Execution Path | Description
System Apps | 66 | SAFE / CAUTION / RECOMMENDED | Path A | Samsung, Google, carrier
Core Apps | 7 | CORE / LOCKED | Path A/B | Confirmation dialog required
User Apps | 13 | SAFE | Path A | Google Play preloads
3rd Party | 19 | SAFE / RECOMMENDED | Path A | Facebook, Microsoft, OEM
Keep (locked) | 5 | KEEP | NONE | Non-removable, grayed out
TOTAL | 110 | — | — | Across 3 device eras (API 21–36)

## ✅ Feature Tracker
⬡ DEBLOATKIT — Feature Tracker
ID | Feature | Category | Description | Status | Priority | Version | Added | Notes
F-001 | 7-Tab Layout | UI | System · Core · User · 3rd Party · Log · Settings · About | Done | P1 | v1.0 | 2026-08-28 | PurgeKit DNA
F-002 | Live Device Polling | ADB | Poll adb devices every 4s — auto detect | Done | P1 | v1.0 | 2026-08-28
F-003 | Device Info Strip | UI | Model, Android, One UI, API, battery | Done | P1 | v1.0 | 2026-08-28
F-004 | USB Debugging Guide | UI | Step-by-step — auto shown on Unauthorized | Done | P1 | v1.0 | 2026-08-28 | Also in About tab
F-005 | Package DB (110+) | Database | JSON DB — Samsung/Google/Facebook/Microsoft | Done | P1 | v1.0 | 2026-08-28 | 3 device eras
F-006 | Single-call Device Scan | ADB | One ADB batch cmd — not 4 separate calls | Done | P1 | v1.0 | 2026-08-29 | 3-8s vs 30s+
F-007 | Risk Badges | UI | SAFE/RECOMMENDED/CAUTION/CORE/LOCKED/KEEP | Done | P1 | v1.0 | 2026-08-28 | Color coded
F-008 | Subcategory Grouping | UI | Green section headers with ✓/✕ per group | Done | P1 | v1.0 | 2026-08-28 | PurgeKit style
F-009 | Select All / Deselect All | UI | Per-tab + per-section bulk selection | Done | P1 | v1.0 | 2026-08-28
F-010 | Disable Selected | ADB | pm disable-user --user 0 — batch | Done | P1 | v1.0 | 2026-08-28 | Path A
F-011 | Uninstall Selected | ADB | pm uninstall -k --user 0 — reversible | Done | P1 | v1.0 | 2026-08-28 | APK stays
F-012 | Re-enable Selected | ADB | Smart restore — enable or install-existing | Done | P1 | v1.0 | 2026-08-29 | Based on prev state
F-013 | Path B (Security Locked) | ADB | pm uninstall --user 0 for Knox/SwiftKey | Done | P1 | v1.0 | 2026-08-28 | One UI 6+
F-014 | Path C SoundAlive Fix | ADB | Force-stop + clear SoundAlive post-debloat | Done | P2 | v1.0 | 2026-08-28 | Optional hook
F-015 | Core Apps Tab | UI | All unchecked, red ⛔ badge | Done | P1 | v1.0 | 2026-08-28
F-016 | Core Confirmation Dialog | UI | Per-app Yes/Cancel before action | Done | P1 | v1.0 | 2026-08-28
F-017 | Auto Silent Backup | Safety | JSON snapshot before every action | Done | P1 | v1.0 | 2026-08-28 | Timestamped
F-018 | Panic Restore | Safety | Re-enable all from latest backup | Done | P1 | v1.0 | 2026-08-28 | Settings tab
F-019 | Battery Warning | Safety | Warn if battery < 20% before debloating | Done | P2 | v1.0 | 2026-08-28
F-020 | Root Detection | ADB | Advisory warning if rooted | Done | P3 | v1.0 | 2026-08-28
F-021 | 4 Themes | UI | Green / Blue / Purple / White | Done | P2 | v1.0 | 2026-08-28 | Settings tab
F-022 | Full Log Tab | Logs | Timestamped ADB log, export to .txt | Done | P1 | v1.0 | 2026-08-28
F-023 | Floating Log Panel | Logs | Overlay log via Log button | Done | P2 | v1.0 | 2026-08-28 | place() overlay
F-024 | Post-action Summary | UI | X succeeded · Y failed · Backup saved | Done | P2 | v1.0 | 2026-08-28
F-025 | Search + Filter | UI | Per-tab search box + subcategory dropdown | Done | P2 | v1.0 | 2026-08-28
F-026 | About Tab + Donate | UI | Author card, PayPal, Razorpay, disclaimer | Done | P2 | v1.0 | 2026-08-28
F-027 | USB Guide in About | UI | Enable/Disable steps + security warning | Done | P2 | v1.0 | 2026-08-29
F-028 | ADB Path Override | Settings | Browse + Test ADB (proper exe vs device test) | Done | P2 | v1.0 | 2026-08-28
F-029 | Backup Folder Override | Settings | Custom path + Open Folder | Done | P3 | v1.0 | 2026-08-28
F-030 | Starts Maximized | UI | state(zoomed) on launch | Done | P2 | v1.0 | 2026-08-29
F-031 | License Agreement Installer | Legal | RTF license shown in Inno Setup | Done | P1 | v1.0 | 2026-08-29 | MIT + disclaimer
F-032 | Chunked Rendering | Performance | 50 rows/chunk, 15ms gap — scroll stays live | Done | P1 | v1.0 | 2026-08-29
F-033 | Package Size Display | UI | Show app size via dumpsys package | Planned | P2 | v1.1 | —
F-034 | Export as Shell Script | Export | Export selected packages as .sh | Planned | P2 | v1.1 | —
F-035 | Wireless ADB Support | ADB | Android 11+ no-USB pairing | Planned | P2 | v1.2 | —
F-036 | Multi-device Support | ADB | Switch between connected devices | Planned | P3 | v1.2 | —
F-037 | Custom Package List Import | Database | Import your own .txt debloat list | Planned | P2 | v1.2 | —
F-038 | 1-Click Presets | UI | Minimal Clean · Bixby Nuke · Privacy Mode | Planned | P1 | v1.2 | —
F-039 | DB Auto-Update | Database | Pull latest packages.json from GitHub | Planned | P3 | v2.0 | —
F-040 | Windows Installer Upgrade | Distribution | Upgrade in-place without uninstall | Planned | P2 | v2.0 | —

## 🐛 Issue Tracker
⬡ DEBLOATKIT — Issue Tracker
ID | Title | Type | Severity | Status | Reported | Resolved | Module | Description | Fix / Notes
I-001 | packages.json comments break json.loads | Bug | Medium | Fixed | 2026-08-28 | 2026-08-28 | app_scanner | JS // comments rejected by stdlib | Strip via re.sub before parse
I-002 | USB guide fires on every poll cycle | Bug | High | Fixed | 2026-08-28 | 2026-08-29 | DebloatKit.py | Unauthorized status repeats every 4s | _usb_guide_shown flag — show once only
I-003 | USB guide grab_set blocks main window | Bug | High | Fixed | 2026-08-28 | 2026-08-29 | DebloatKit.py | App froze when device disconnected mid-guide | Removed grab_set — guide non-blocking
I-004 | SecurityException not caught on disable | Bug | High | Fixed | 2026-08-28 | 2026-08-28 | adb_manager | Path A fails silently on Knox pkgs | Detect exception string, return security_exception
I-005 | Re-enable used wrong command | Bug | High | Fixed | 2026-08-29 | 2026-08-29 | adb_manager | pm enable used for uninstalled pkgs (wrong) | restore_package() checks previous state
I-006 | Tab switching lag — 540 pkg freeze | Bug | Critical | Fixed | 2026-08-29 | 2026-08-29 | DebloatKit.py | All rows created synchronously — UI frozen | Chunked render 50 rows/15ms gap
I-007 | Scrollbar frozen during render | Bug | High | Fixed | 2026-08-29 | 2026-08-29 | DebloatKit.py | after(1ms) too fast, UI cant process events | after(15ms) — one display frame gap
I-008 | Scan took 30+ seconds | Bug | High | Fixed | 2026-08-29 | 2026-08-29 | app_scanner | 4 separate ADB calls — each 3-8s | Single batch shell command — 1 roundtrip
I-009 | Settings page overlaps package list | Bug | High | Fixed | 2026-08-28 | 2026-08-29 | DebloatKit.py | Both frames packed simultaneously | _show_pkg_ui/_show_page_ui pack_forget pattern
I-010 | ADB Test says OK without device | Bug | Medium | Fixed | 2026-08-29 | 2026-08-29 | DebloatKit.py | adb version runs without device | Now checks adb devices — shows no-device msg
I-011 | Error 740 on exe launch | Bug | Critical | Fixed | 2026-08-28 | 2026-08-29 | build.bat | --uac-admin + PrivilegesRequired=admin conflict | Removed --uac-admin, PrivilegesRequired=lowest
I-012 | ISS ifdef FileExists() parse error | Bug | High | Fixed | 2026-08-28 | 2026-08-28 | DebloatKit_Installer.iss | ifdef doesnt accept function calls | Removed conditional icon block
I-013 | Compact toggle did nothing | Bug | High | Fixed | 2026-08-28 | 2026-08-29 | DebloatKit.py | compact_var logic inverted | Removed feature — always compact layout
I-014 | Theme rebuild caused app crash | Bug | Medium | Fixed | 2026-08-28 | 2026-08-29 | DebloatKit.py | Device polling callbacks after widget destroy | try/except on all callbacks
I-015 | Disconnect didnt clear tab state | Bug | Medium | Fixed | 2026-08-29 | 2026-08-29 | DebloatKit.py | Old packages stayed visible after unplug | _on_device_disconnected clears app_data
I-016 | No license agreement in installer | Enhancement | Medium | Fixed | 2026-08-29 | 2026-08-29 | DebloatKit_Installer.iss | No MIT/disclaimer shown at install | Added LICENSE.rtf + LicenseFile directive
I-017 | About page had phantom empty widget | Bug | Low | Fixed | 2026-08-28 | 2026-08-29 | DebloatKit.py | CTkFrame.__init__ line created invisible widget | Removed — restructured About layout
I-018 | installer/ folder still in zip | Bug | Low | Fixed | 2026-08-29 | 2026-08-29 | build | Old installer/ subfolder in zip after moving files | rm -rf installer/ before repackage
I-019 | Subcategory filter resets on re-scan | Enhancement | Low | Open | 2026-08-29 | — | DebloatKit.py | Filter resets to All after scan | Save + restore filter state across scan
I-020 | Battery parse fails on some ROMs | Bug | Low | Open | 2026-08-29 | — | adb_manager | dumpsys battery format varies by ROM | Add alternate parsers for different formats
I-021 | No multi-device support | Enhancement | Medium | Planned | 2026-08-29 | v1.2 | adb_manager | Only first connected device used | Device selector dropdown in topbar

## 🐙 GitHub
⬡ DEBLOATKIT — GitHub Repository Reference
REPOSITORY DETAILS
Repo Name | DebloatKit
URL | https://github.com/yashwanthramsomireddy/DebloatKit
Visibility | Public
License | MIT
Description | ADB debloater for Samsung Galaxy devices. Disable & uninstall bloatware safely without root. Works with One UI 5 through One UI 9.
Default Branch | main
TOPICS / TAGS
android
debloater
samsung
galaxy
oneui
adb
bloatware
python
customtkinter
windows
toolkit
teamexykings
RELEASE HISTORY
Tag | Title | Date | Type | Notes
v1.0 | DebloatKit v1.0 — Initial Release | 2026-08-29 | Release | 110+ packages. 7 tabs. Core confirmation. Auto backup. License agreement installer.
FIRST PUSH COMMANDS
git init && git add .
git commit -m "feat: initial release v1.0"
git branch -M main
git remote add origin https://github.com/yashwanthramsomireddy/DebloatKit.git
git push -u origin main
git tag v1.0 && git push origin v1.0
FILE STRUCTURE
DebloatKit.py | Main entry — full UI, all 7 tabs, event wiring
core/adb_manager.py | ADB bridge — polling, batch props, Path A/B/C
core/app_scanner.py | Single-call device scan + DB cross-reference
core/debloater.py | Disable/uninstall/restore/backup engine
ui/themes.py | Green/Blue/Purple/White color tokens
data/packages.json | 110+ packages — risk ratings, eras, paths
assets/icon.ico | App icon — all sizes (16–256px)
LICENSE.rtf | RTF license for Inno Setup agreement page
DebloatKit_Installer.iss | Inno Setup installer script
build.bat | Build exe — one double-click
build_installer.bat | Build setup .exe after build.bat
backups/ | Auto-created — timestamped JSON backups

## 💰 Donations
⬡ DEBLOATKIT — Donation & Revenue Tracker
DONATION CHANNELS
Platform | Link / ID | Type | Status | Currency | Monthly Goal | Notes
PayPal | https://paypal.me/yash92duster | One-time | Active | USD | — | International users
Razorpay | https://rzp.io/rzp/nsogoeD | One-time / Monthly | Active | INR | ₹1,000 | Indian users — UPI, cards, netbanking
GitHub Sponsors | github.com/sponsors/yashwanthramsomireddy | Monthly | Planned | USD | — | Set up after 100 stars
DONATION LOG
Date | Platform | Amount | Currency | Message | Donor | Thank You Sent
2026-08-29 | Razorpay | 100 | INR | First supporter! | — | ✓
SUMMARY
Total Donations (₹) | 0
Total Donations ($) | 0
Total Supporters | 1

## 📱 Device Compat
⬡ DEBLOATKIT — Device Compatibility Matrix
Era | Device Series | Android | One UI | API Level | Status | Packages | Notes
1 — Legacy TouchWiz | Galaxy S5, S6, S7, S8, S9 | 5.0 – 8.1 | TouchWiz / Grace UX | 21 – 27 | Supported | ~15 | Legacy bloat — Gear VR, S Health, Briefing
2 — Mid One UI | Galaxy S10 – S23 Note 10, Note 20 Z Fold 1–5, Z Flip 1–5 | 9 – 13 | One UI 1.x – 5.x | 28 – 33 | Fully Supported | ~70 | Main era — Bixby, AR, Gaming Hub, Knox
3 — Modern One UI | Galaxy S24, S25, S26 Ultra Z Fold 6, 7, 8 Ultra | 14 – 16 | One UI 6.x – 9 | 34 – 36 | Fully Supported | ~95 | Security-locked pkgs — Path B used